## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Michael | Joshua | Mao | Toni | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Coding | [12 empty] | 0
Iteration 1: | Development | [11 empty] | 0
|  | Requirement document | Project Manager | Toni | 2
|  | Research and learn .Net, Bootstrap, SQL | Team | All | 30
|  | Set up local server | Developer | Michael, | 10
|  | Set up CSS framework | Developer | Michael, Joshua | 10
|  | Create Home Page | Developer | Mao, Joshua | 15
|  | Home Page-Dashboard | Developer | Michael, Joshua | 15
|  | Create Login Page-Password fields & Login button | Developer | Michael, Mao | 10
|  | Store user information locally in the database | Developer | Michael, Mao | 12
|  | Project Charter | Project Manager | Toni | 1
| Design | [11 empty] | 0
|  | User interface design/ prototype | Developer | Toni, | 8
|  | Team meeting | Team | ALL | 4
|  | Database research/design | Developer | Mao | 5