## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Michael | Joshua | Mao | Toni | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Coding | [12 empty] | 0
Iteration 1: | Development | [11 empty] | 0
|  | Requirement document | Project Manager | Toni | 2 | 4 | 4 | 4 |  |  |  | 4
|  | Research and learn .Net, Bootstrap, SQL | Team | All | 30 | 90 |  | 9 | 8 |  |  | 1
|  | Set up local server | Developer | Michael, | 10 | 10 | 5 | 5 | 5
|  | Write basic proxy code | Developer | Michael, Joshua | 10 | 20 | 3 | 3 | 3
|  | Create Http handling code for Homepage | Developer | Mao, Joshua | 10 | 20 | 4 | 9 | 4 |  | 5
|  | Create Login Page-Implement Code | Developer | Michael, Mao | 10 | 20 |  | 8 | 3 |  | 5
|  | Store user information locally in the database | Developer | Michael, Mao | 12 | 24 |  | 8 | 3 |  | 5
|  | Project Charter | Project Manager | Toni | 1 | 1 | 2 | 2 |  |  |  | 2
| Design | [11 empty] | 0
|  | User interface design/ prototype | Developer | Toni, | 8 | 8 | 4 | 4 |  |  |  | 4
|  | Team meeting | Team | ALL | 4 | 4 |  | 4 | 1 | 1 | 1 | 1
|  | Database research/design | Developer | Mao | 5 | 5 | 3 | 3 |  |  | 3
Iteration 2: | Design | [8 empty] | 0
|  | Project plan document | Project Manager | Toni | 5 | 5
|  | Dashboard, setting page interface | Developer | Toni | 5 | 5
|  | Design HTTP& CSS format/structure | Developer | Mao, Michael | 2 | 4
|  | Design Http & CSS handling code | Developer | Mao, Joshua | 1 | 1
|  | Create UI design that is suitble for all screens | Developer | Toni | 2 | 4
| Development | [8 empty] | 0
|  | Review Overall Implementation requirements | Developer | Michael, Joshua | 15 | 15
|  | Create and finish Http code for Homepage Dashboard | Developer | Mao, Michael | 3 | 3
|  | Handle/Modify Http&Css data structure for retrieving balance | Developer | Mao, Joshua | 2 | 2
|  | Create Login Page-Password fields & Login button | Developer | Michael, Joshua | 5 | 5
|  | Implement UI | Developer | Michael, Joshua | 10 | 10
|  | Team meeting | Team | All | 1 | 1
| Analysis | [8 empty] | 0
|  | Bug fix as required | Tester, Developer | Mao | 3 | 3
|  | Evaluate needs for next iteration | Project Manager | Toni | 1 | 1