## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Michael | Joshua | Mao | Toni | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 85 |  | 48 |  |  |  |  | 0
|  | Requirement document | Project Manager | Toni | 2 |  | 4 |  |  |  |  | 4 | 4
|  | Research and learn .Net, Bootstrap, SQL | Team | All | 30 |  | 9 |  | 4 | 3 | 1 | 1 | 9
|  | Set up local server | Developer | Michael, | 10 |  | 5 |  | 5 |  |  |  | 5
|  | Write basic proxy code | Developer | Michael, Joshua | 10 |  | 3 |  | 2 | 1 |  |  | 3
|  | Create Http handling code for Homepage | Developer | Mao, Joshua | 10 |  | 9 |  | 3 | 1 | 5 |  | 9
|  | Create Login Page-Implement Code | Developer | Michael, Mao | 10 |  | 8 |  | 3 |  | 5 |  | 8
|  | Store user information locally in the database | Developer | Michael, Mao | 12 |  | 8 |  | 3 |  | 5 |  | 8
|  | Project Charter | Project Manager | Toni | 1 |  | 2 |  |  | 1 |  | 2 | 3
| Design |  |  |  |  | 17 | 0 | 11 |  |  |  |  | 0
|  | User interface design/ prototype | Developer | Toni, | 8 |  | 4 |  |  |  |  | 4 | 4
|  | Team meeting | Team | ALL | 4 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Database research/design | Developer | Mao | 5 |  | 3 |  |  |  | 3 |  | 3
Iteration 2: | Design |  |  |  |  | 15 |  | 21 |  | 0
|  | Project plan document | Project Manager | Toni | 5 |  | 5 |  |  |  | 1 | 4 | 5
|  | Dashboard, setting page interface | Developer | Toni | 5 |  | 3 |  |  |  |  | 3 | 3
|  | Design HTTP& CSS format/structure | Developer | Mao, Michael | 2 |  | 8 |  | 5 |  | 3 |  | 8
|  | Design Http & CSS handling code | Developer | Mao, Joshua | 1 |  | 4 |  |  | 1 | 3 |  | 4
|  | Create UI design that is suitble for all screens | Developer | Toni | 2 |  | 2 |  |  |  |  | 2 | 2
| Development |  |  |  |  | 36 |  | 35 |  | 0
|  | Review Overall Implementation requirements | Developer | Michael, Joshua | 5 |  | 2 |  | 2 |  |  |  | 2
|  | Create and finish Http code for Homepage Dashboard | Developer | Mao, Michael | 3 |  | 7 |  | 4 |  | 3 |  | 7
|  | Handle/Modify Http&Css data structure for retrieving balance | Developer | Mao, Joshua | 2 |  | 5 |  | 3 | 2 | 3 |  | 5
|  | Create Login Page-Password fields & Login button | Developer | Michael, Joshua | 5 |  | 8 |  | 7 | 1 |  |  | 8
|  | Implement UI | Developer | Michael, Joshua | 5 |  | 6 |  | 5 | 1 |  |  | 6
|  | Team meeting | Team | All | 1 |  | 4 |  | 1 | 1 | 1 | 1 | 4
| Analysis |  |  |  |  | 4 |  | 4 |  | 0
|  | Bug fix as required | Tester, Developer | Mao | 3 |  | 3 |  |  |  | 3 |  | 3
|  | Evaluate needs for next iteration | Project Manager | Toni | 1 |  | 1 |  |  |  |  | 1 | 1
Iteration 3: | Development |  |  |  |  | 22 |  | 21 |  |  |  |  | 0
|  | Learn toolset(visual studio) | Developer | Joshua, Mao | 5 |  | 4 |  |  | 2 | 2 |  | 4
|  | Review requirements | All | ALL | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Develope and implement code for notification rules(Out of state transactions) | Developer | Mao, Michael | 2 |  | 2 |  | 1 |  | 1 |  | 2
|  | Develop code for notification rules(Timeframe usage) | Developer | Michael, Joshua | 2 |  | 3 |  | 2 | 1 |  |  | 3
|  | Develop code for notification rules(Categories) | Developer | Mao | 2 |  | 2 |  | 1 |  | 1 |  | 2
|  | Handle/Modify Http & Css code for homepage according to design changes | Developer | Michael, Toni | 3 |  | 2 |  | 1 |  |  | 1 | 2
|  | Unit Testing | Developer | Mao | 3 |  | 3 |  |  |  | 2 |  | 3
|  | Learn how to export spreadsheet on a webpage | ALL | ALL | 3 |  | 1 |  | 1 |  |  |  | 1
| Design |  |  |  |  | 3 | 0 | 5 |  |  |  |  | 0
|  | Risk Analysis | Project Manager | Toni,Mao | 2 |  | 3 |  |  |  | 1 | 2 | 3
|  | Adjust prototype (ex. user interface design) | Development | Toni,Mao | 1 |  | 2 |  |  |  | 1 | 1 | 2
| Analysis |  |  |  |  | 7 | 0 | 16 |  |  |  |  | 0
|  | Architecture Document | Team | ALL | 2 |  | 11 |  | 1 | 1 | 3 | 6 | 11
|  | Update project plan and requirements doc | Project Manager | Toni | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Update Iteration spreadsheet | Project Manager | Toni | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Online team meeting | Team | ALL | 3 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 4: | Design |  |  |  |  | 12 |  | 11 |  | 0 |  |  | 11
|  | Adjust prototype.Login page user interface | Project Manager | Toni | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Adjust prototype base on presentation feedback | Project Manager | Toni | 2 |  | 2 |  |  |  |  | 2 | 2
|  | Architecture document design | Developer | Mao,Michael | 2 |  | 2 |  | 1 |  | 1 |  | 2
|  | Change Http/CSS web page strcture to accomendate users needs | Developer | Mao,Jushua | 2 |  | 3 |  |  | 1 | 2 |  | 3
|  | CSS implement for log in page | Developer | Joshua | 3 |  | 1 |  |  | 1 |  |  | 1
|  | Database and webpage connection structure design | Developer | Michael,Toni | 2 |  | 3 |  | 1 |  |  | 2 | 3
| Development |  |  |  |  | 26 |  | 28 |  | 0
|  | Learn how to develope code for notification rules(Out of state transactions) | Developer | Mao, Michael | 3 |  | 4 |  | 1 |  | 3 |  | 4
|  | Learn developing code for notification rules(Timeframe usage) | Developer | Michael, Joshua | 3 |  | 2 |  | 1 | 1 |  |  | 2
|  | Leran developing code for notification rules(Categories) | Developer | Mao | 3 |  | 3 |  |  |  | 3 |  | 3
|  | learn more about .NET framework | Team | All | 5 |  | 3 |  | 1 | 1 | 1 | 1 | 3
|  | Write querries in Microsoft SQL | Developer | Mao,Toni | 2 |  | 6 |  |  |  | 2 | 4 | 6
|  | Learn about the connection between webpage and database | Developer | Mao,Michael | 2 |  | 5 |  | 2 |  | 3 |  | 5
|  | Implement transaction summary display on webpage | Developer | Michael | 3 |  | 2 |  | 2 |  |  |  | 2
|  | Learn how to write code to export spreadsheet on a webpage | Developer | Michael | 2 |  | 3 |  | 3 |  |  |  | 3
|  | Unit testing for c# code | Developer | Joshua | 3 |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 3 |  | 8 |  | 0 |  |  | 8
|  | Update iteration spreadsheet | Team | All | 1 |  | 4 |  | 1 | 1 | 1 | 1 | 4
|  | Online meeting for risk analysis in the project | Team | All | 2 |  | 4 |  | 1 | 1 | 1 | 1 | 4
Iteration 5: | Development |  |  |  |  | 19 | [6 empty] | 0
|  | Database Trigger Out of state transaction implemention | Developer | Toni, Mao | 1
|  | Learn about the connection between webpage and database | Team | All | 3
|  | Write c# code in .Net to connect Database to webpage | Developer | Mao, Michael | 1
|  | Implemente code for Notification rules (Location) | Developer | Mao,jushua | 2
|  | Implemente code for Notification rules (Timeframe) | Developer | Joshua, Michael | 2
|  | Implemente code for Notification rules (Categories) | Developer | Michael | 2
|  | Attempt to implement code to export spreadsheet on a webpage | Developer | Michael | 3
|  | Unit testing for c# code | Developer | Mao | 5
| Design |  |  |  |  | 10 | 0 | [5 empty] | 0
|  | Database Trigger design | Developer | Toni, Mao | 1
|  | Adjust prototype.Login page user interface | Project Manager | Toni | 3
|  | Adjust prototype base on presentation feedback | Project Manager | Toni | 3
| Analysis |  |  |  |  | 15 | 0 | [5 empty] | 0
|  | Test Plan | Team | All | 5
|  | User and System Guide | Project Manager | Toni | 5
|  | Online team meeting | Team | All | 3
|  | Iteration update | Team | All | 2